## 01 Dashboard
Climate-Health Programme Umbrella Workbook
Working Draft v0.1.0 ¦ Programme owner: WHO ¦ Status: Not yet approved as an official WHO publication
Purpose and use |  |  | Programme snapshot
Purpose | Coordinate the umbrella climate-health programme and maintain traceability across HHAS and CHUD. |  | Metric | Value | Interpretation | Status | Count | % of components
How to use | Update programme components, actors, workflows, requirements, risks, validation evidence and country adaptation records. |  | Programme components | 9 | Registered umbrella, HHAS and CHUD components | Draft | 9 | 100%
Status convention | Use the controlled status values provided in dropdown fields. Draft entries should not be treated as approved. |  | Open risks | 3 | Risks requiring action | Under review | 0 | 0%
IDs | Preserve stable IDs once assigned. Do not recycle IDs after an item is retired or superseded. |  | Open assumptions | 1 | Assumptions not yet closed | Approved | 0 | 0%
Country adaptation | Record whether each generic component is adopted, adapted, mapped, deferred or not applicable. |  | Requirements registered | 7 | Umbrella-level requirements | Validated | 0 | 0%
Review principle | Draft early, expose assumptions, review in parallel and correct collaboratively while preserving quality and authority. |  | Validation records | 5 | Tests, reviews and evidence items | Deferred | 0 | 0%
|  |  | Country adaptations | 5 | Recorded national mappings or decisions
Programme principles
1 | Country ownership | Countries retain authority over institutions, data, thresholds, operations and publication.
2 | Connected capabilities | CHUD governs the evidence layer; HHAS converts approved evidence into warnings and coordinated action.
3 | Visible assumptions | Working assumptions remain explicit until confirmed, rejected or replaced.
4 | Traceability | Every material component links to its source, workflow, requirement, test and country adaptation.
5 | Proportionate implementation | Reuse existing systems and introduce only capabilities that can be governed and maintained.

## 02 Programme Components
Programme Components Register
Component ID | Programme Layer | Component | Purpose | Primary Owner | Related Artefact | Priority | Status | Version | Country Configurable | Source / Basis | Notes
UMB-CMP-001 | Umbrella | Programme governance | Define programme ownership, decision authority and cross-sector coordination. | WHO / country lead | Umbrella prompts 1–8 | Mandatory | Draft | 0.1.0 | Yes | Preliminary programme architecture | Programme-level governance; country roles require mapping.
UMB-CMP-002 | Umbrella | Programme scope and boundaries | Define what the programme covers and excludes. | WHO / country lead | Umbrella scope | Mandatory | Draft | 0.1.0 | Yes | Preliminary programme architecture | Keep predictive models outside core CHUD unless separately approved.
UMB-CMP-003 | Umbrella | Cross-programme traceability | Link evidence, workflows, requirements, tests and country adaptations. | Programme management | Crosswalk register | Mandatory | Draft | 0.1.0 | Yes | DAK methodology | Implemented through this workbook and detailed HHAS/CHUD workbooks.
HHAS-CMP-001 | HHAS | Heat-health warning lifecycle | Support monitoring, assessment, approval, dissemination, update and cancellation. | Health authority | HHAS sections 5, 7, 8 | Mandatory | Draft | 0.1.0 | Yes | HHAS draft | Warning levels and thresholds are country configured.
HHAS-CMP-002 | HHAS | Institutional actions | Connect warning states to role-specific actions. | Health authority | HHAS interventions and workflows | Mandatory | Draft | 0.1.0 | Yes | HHAS draft | Includes health, social care, municipalities, employers and public.
CHUD-CMP-001 | CHUD | Governed source acquisition | Register and acquire climate, health, environmental and geographic data. | Data owner / steward | CHUD sections 5, 6, 8 | Mandatory | Draft | 0.1.0 | Yes | CHUD draft | Supports automated and controlled manual acquisition.
CHUD-CMP-002 | CHUD | Temporal and spatial harmonisation | Align data across periods, time zones, grids and administrative areas. | Data / geospatial lead | CHUD sections 7, 10, 11 | Mandatory | Draft | 0.1.0 | Yes | CHUD draft | Methods require country and scientific validation.
CHUD-CMP-003 | CHUD | Fitness for use and publication | Assess suitability, limitations, release and correction. | Public health institute | CHUD sections 9–12 | Mandatory | Draft | 0.1.0 | Yes | CHUD draft | Version-specific approval required.
UMB-CMP-004 | Umbrella | Demonstration and case studies | Illustrate end-to-end implementation and compare real-world practice. | Programme team | Agara + companion documents | High | Draft | 0.1.0 | Yes | Agara synthetic demonstration | Agara is synthetic; real cases require cited evidence.

## 03 Actors
Programme Actors and Institutional Responsibilities
Actor ID | Layer | Generic Actor / Persona | Institution Type | Core Responsibilities | Decision Authority | Data Responsibility | Primary Interfaces | Country Role Mapping | Status | Validation Notes
ACT-001 | Umbrella | Programme owner | WHO / national lead | Set programme direction, approve scope and coordinate partners. | Programme-level decisions | Programme oversight and reporting | Health, meteorological, digital and funding partners |  | Draft | Map to actual national authority.
ACT-002 | Umbrella | Country programme coordinator | Ministry / public health institute | Coordinate implementation, decisions, reviews and roadmap. | Operational coordination | Country register and evidence | All country actors |  | Draft | May be a dedicated role or assigned function.
ACT-003 | Shared | National meteorological service | Meteorological authority | Provide observations, forecasts, metadata and revisions. | Authority over meteorological products | Climate and weather sources | CHUD pipelines; HHAS risk review |  | Draft | Confirm service catalogue and access method.
ACT-004 | Shared | National public health institute | Public health authority | Interpret evidence, conduct surveillance and support risk decisions. | Scientific and public-health advice | Health surveillance and analytical outputs | CHUD and HHAS |  | Draft | Could sit within ministry in some countries.
ACT-005 | CHUD | Data steward | Source-owning institution | Maintain definitions, metadata, quality and permitted use. | Data stewardship decisions | Assigned dataset/domain | Data owner, pipeline operator, analyst |  | Draft | Ownership and stewardship should remain distinct.
ACT-006 | CHUD | Data pipeline operator | Health information centre / technical team | Run acquisition, validation, harmonisation and integration. | Operational processing within approved controls | Pipeline logs and generated datasets | Data stewards and analysts |  | Draft | May be central, local or federated.
ACT-007 | HHAS | Warning authority | Ministry / designated authority | Approve, update, extend and cancel official warnings. | Official warning decision | Warning records and approvals | Meteorological and public-health reviewers |  | Draft | Legal mandate must be confirmed.
ACT-008 | HHAS | District health focal point | Subnational health authority | Validate local conditions, coordinate action and report implementation. | District operational escalation | Local health and implementation information | Facilities, municipalities and national team |  | Draft | Key for country groundtruthing.
ACT-009 | Shared | Funding and implementation partner | Donor / UN / technical partner | Provide finance, technical support, milestones and review. | Defined by agreement | Programme reports and evidence | Programme owner and country lead |  | Draft | Partner satisfaction should not override country ownership.

## 04 Workflows
Programme-Level Workflow Catalogue
Workflow ID | Layer | Workflow | Trigger | Start Actor | Key Stages | Primary Output | Dependencies | Exception / Fallback | Frequency | Owner | Status
UMB-WFL-001 | Umbrella | Define and approve programme scope | Programme initiation or material change | Programme owner | Draft scope; consult actors; record assumptions; approve boundaries | Approved programme scope | Governance and evidence | Defer unresolved scope items with owner and review date | At initiation and change | Programme owner | Draft
UMB-WFL-002 | Umbrella | Country groundtruthing and adaptation | Country selected for implementation | Country coordinator | Assess readiness; map roles, sources and workflows; validate; approve adaptations | Country implementation package | Country participation and data access | Use visible gaps and interim methods | Pilot and periodic review | Country lead | Draft
UMB-WFL-003 | Umbrella | Programme change control | New evidence, country finding or defect | Programme coordinator | Assess impact; review; approve/reject; update versions; communicate | Controlled programme change | Traceability and validation | Emergency change with retrospective review | Event-driven | Programme coordinator | Draft
HHAS-WFL-001 | HHAS | Generate and approve heat-health warning | Forecast or health-risk signal | Meteorological / surveillance actor | Acquire evidence; assess risk; expert review; approve; issue | Versioned warning and actions | CHUD dataset; warning authority | Manual review and communication fallback | Event-driven | Warning authority | Draft
HHAS-WFL-002 | HHAS | Monitor, update and cancel warning | Active warning and new evidence | HHAS coordinator | Monitor evidence; reassess; update/extend/de-escalate; cancel; archive | Current warning status | Forecasts, health signals, implementation reports | Manual monitoring if systems unavailable | During event | HHAS coordinator | Draft
CHUD-WFL-001 | CHUD | Acquire and validate sources | Scheduled or event source delivery | Pipeline operator | Receive; verify; validate; classify; quarantine or accept | Validated source dataset | Source access and schedule | Retry, fallback or manual receipt | Per source schedule | Data operations | Draft
CHUD-WFL-002 | CHUD | Harmonise and integrate datasets | Validated source versions available | Pipeline operator | Standardise; align time; map geography; integrate; reconcile | Versioned integrated dataset | Rules, crosswalks, quality gates | Hold, partial internal output or review | Per approved pipeline | Data operations | Draft
CHUD-WFL-003 | CHUD | Correct and reprocess outputs | Confirmed source or method defect | Data steward | Assess impact; correct; reprocess; review; republish/withdraw | Corrected current version | Lineage and authority | Publication hold and user notification | Event-driven | Data steward | Draft

## 05 Programme Requirements
Umbrella Functional and Governance Requirements
Requirement ID | Layer | Requirement | Rationale | Priority | Implementation Mode | Owner | Related Workflow | Acceptance Criterion | Country Adaptation | Status | Evidence
UMB-REQ-001 | Umbrella | The programme shall maintain approved scope, ownership and decision authority. | Prevents technical work from proceeding without institutional legitimacy. | Mandatory | Governance process | Programme owner | UMB-WFL-001 | Approved scope identifies owner, boundaries, decision route and review date. | Required | Draft
UMB-REQ-002 | Umbrella | The programme shall maintain end-to-end traceability across umbrella, HHAS and CHUD artefacts. | Supports impact analysis, validation and controlled change. | Mandatory | Workbook / registry | Programme coordinator | UMB-WFL-003 | A sampled component can be traced to source, workflow, requirement, test and country adaptation. | Required | Draft
UMB-REQ-003 | Umbrella | Country adaptations shall be recorded separately from generic programme content. | Avoids presenting national decisions as universal standards. | Mandatory | Workbook / process | Country coordinator | UMB-WFL-002 | Each adapted component includes rationale, owner and validation status. | Required | Draft
UMB-REQ-004 | Shared | The programme shall distinguish documented practice, programme interpretation and illustrative assumptions. | Protects legitimacy of case studies and demonstrations. | Mandatory | Documentation control | Programme owner | UMB-WFL-003 | Demonstration and case-study content uses explicit classification. | Required | Draft | Agara demonstration
UMB-REQ-005 | Shared | The programme shall support central, local, federated and hybrid implementation models. | Countries differ in ownership, privacy and infrastructure. | High | Architecture and configuration | Architecture lead | UMB-WFL-002 | Country design records data location and selected deployment model. | Required | Draft
UMB-REQ-006 | Shared | Material AI-supported outputs shall remain traceable and subject to accountable human review. | AI must remain subordinate to scientific and public-health authority. | Mandatory | Architecture and governance | Programme owner | UMB-WFL-003 | AI use case identifies model, inputs, reviewer, decision and fallback. | As applicable | Draft
UMB-REQ-007 | Umbrella | The programme shall track partner commitments, milestones, financing dependencies and handover. | Supports accountable delivery and sustainability. | High | Programme management | Programme coordinator | UMB-WFL-002 | Each funded workstream has owner, milestone, resource need and transition plan. | Required | Draft

## 06 HHAS-CHUD Crosswalk
HHAS–CHUD Programme Crosswalk
Crosswalk ID | Programme Objective | Umbrella Component | HHAS Component | CHUD Component | Shared Data / Evidence | Primary Workflow | Indicator / Measure | Requirement | Country Configuration | Validation Evidence | Gap / Action
XWK-001 | Convert climate information into coordinated public-health action | Programme governance | Warning generation and action activation | Governed source acquisition and integrated dataset | Forecasts, observed weather, health pressure, vulnerability | HHAS-WFL-001 | Warning lead time; acknowledgement; pipeline quality | UMB-REQ-001; UMB-REQ-002 | Warning authority, risk method and channels |  | Confirm country decision authority.
XWK-002 | Preserve evidence integrity from source to publication | Traceability and change control | Warning versioning and superseding | Lineage, versioning, correction and reprocessing | Source versions, rules, approvals and publication records | CHUD-WFL-003 | Correction time; current-version accuracy | UMB-REQ-002 | Retention, correction authority and notification |  | Populate detailed HHAS/CHUD workbook links.
XWK-003 | Support country ownership and adaptation | Country implementation governance | Country-configured warning levels and actions | Country-configured sources, calendars, geography and quality rules | Country readiness and adaptation evidence | UMB-WFL-002 | Adaptations validated; critical gaps open | UMB-REQ-003; UMB-REQ-005 | All country-specific settings |  | Pilot-country mapping pending.
XWK-004 | Demonstrate the end-to-end model | Case studies and demonstrations | Agara warning and response lifecycle | Agara data acquisition, harmonisation and integration | Synthetic event evidence and acceptance tests | HHAS-WFL-001; CHUD-WFL-002 | Demonstration coverage and identified gaps | UMB-REQ-004 | Illustrative settings must be labelled |  | Agara completed as initial demonstration.
XWK-005 | Support sustainable programme delivery | Partner and financing governance | Operational staffing and communication capacity | Hosting, data access, support and maintenance capacity | Milestones, expenditure, partner feedback and handover | UMB-WFL-002 | Milestone completion; ownership confirmed | UMB-REQ-007 | Funding and partner arrangements |  | Define programme-level partner satisfaction measures.

## 07 Country Adaptation
Country Adaptation Register
Adaptation ID | Country | Generic Component ID | Generic Component | National Component / Decision | Adaptation Status | Responsible Institution | Current State | Target State | Priority | Dependency | Validation Status | Evidence / Reference | Notes
ADP-001 | Pilot Country 1 | UMB-CMP-001 | Programme governance |  | To assess |  |  |  | Mandatory |  | Not started |  | Confirm lead institution and decision route.
ADP-002 | Pilot Country 1 | ACT-003 | National meteorological service |  | To assess |  |  |  | Mandatory |  | Not started |  | Confirm source products and access.
ADP-003 | Pilot Country 1 | HHAS-CMP-001 | Heat-health warning lifecycle |  | To assess |  |  |  | Mandatory |  | Not started |  | Determine whether an existing warning service can be adapted.
ADP-004 | Pilot Country 1 | CHUD-CMP-002 | Temporal and spatial harmonisation |  | To assess |  |  |  | Mandatory |  | Not started |  | Confirm reporting calendars and geographic boundary sources.
ADP-005 | Pilot Country 2 | UMB-CMP-001 | Programme governance |  | To assess |  |  |  | Mandatory |  | Not started |  | Country groundtruthing pending.

## 08 Risks Decisions
Risks, Assumptions and Decisions Register
Record ID | Record Type | Title | Description | Impact | Likelihood | Owner | Status | Target / Review Date | Decision / Mitigation | Affected Components | Evidence / Source
RAD-001 | Assumption | Programme owner and governance | WHO owns the generic programme package; country authorities own national implementation decisions. | High | Medium | Programme owner | Open | 2026-09-30 | Confirm governance with programme leadership. | UMB-CMP-001; UMB-REQ-001 | Working draft assumption
RAD-002 | Risk | Public documentation gaps in real-world cases | Published case studies may not contain detailed data flows, thresholds, costs or approval routes. | Medium | High | Case-study lead | Open | 2026-10-31 | Label gaps explicitly and convert them into groundtruthing questions. | UMB-CMP-004 | Case-study document
RAD-003 | Risk | Over-complex preliminary package | Too many detailed artefacts may discourage early reviewers. | Medium | Medium | Programme coordinator | Mitigating | 2026-08-31 | Use three consolidated workbooks and concise publication sections. | All | Workbook design decision
RAD-004 | Decision | Workbook grouping | Use one umbrella workbook, one HHAS workbook and one CHUD workbook. | Medium | Low | Programme coordinator | Closed | 2026-08-03 | Apply consistent IDs, formats and traceability across all three. | All | User decision
RAD-005 | Assumption | Pilot-country selection | Two pilot countries will groundtruth the generic package through March 2027. | High | Medium | Programme owner | Open | 2026-09-30 | Confirm countries, sponsors and implementation scope. | UMB-WFL-002 | Programme planning assumption
RAD-006 | Risk | Unsupported normative thresholds | Illustrative thresholds could be mistaken for WHO recommendations. | High | Medium | Technical leads | Mitigating | 2026-08-31 | Label all demonstration values as illustrative and country configurable. | HHAS-CMP-001; UMB-REQ-004 | Agara demonstration

## 09 Validation Evidence
Validation and Evidence Register
Evidence ID | Validation Domain | Component / Requirement | Validation Activity | Method | Expected Result | Actual Result | Status | Reviewer | Evidence Location | Date | Follow-up Action
VAL-001 | Governance | UMB-REQ-001 | Review programme scope and authority | Document and stakeholder review | Owner, boundaries and decision route confirmed |  | Planned |  |  |  | Schedule leadership review.
VAL-002 | Traceability | UMB-REQ-002 | Trace sample Agara elements across programme, CHUD and HHAS | Workbook inspection | Each sampled element links to workflow, requirement and test |  | Planned |  |  |  | Complete after HHAS and CHUD workbooks.
VAL-003 | Country adaptation | UMB-WFL-002 | Groundtruth generic actors and workflows in Pilot Country 1 | Workshop and source-system walkthrough | Roles, data sources and gaps confirmed |  | Not started |  |  |  | Await country selection.
VAL-004 | Demonstration | UMB-REQ-004 | Review Agara classifications and disclaimers | Technical and editorial review | Documented concepts, DAK interpretation and illustrative assumptions are distinguishable |  | In progress |  | Agara demonstration | 2026-08-03 | Resolve terminology before publication.
VAL-005 | Workbook usability | All umbrella sheets | Review navigation, filters, IDs and dropdown fields | User review | Workbook is understandable and usable without specialist spreadsheet skills |  | Planned |  |  |  | Use feedback before building HHAS workbook.

## 10 Change Log
Workbook Change Log
Change ID | Date | Workbook Version | Affected Sheet / Component | Change Type | Change Summary | Reason | Requested By | Approved By | Status | Next Action
CHG-001 | 2026-08-03 | 0.1.0 | Entire workbook | Initial creation | Created consolidated programme umbrella workbook. | Provide practical programme register and traceability structure. | Christopher Jones |  | Implemented | Review structure before HHAS workbook.
CHG-002 | 2026-08-03 | 0.1.0 | Demonstrations and case studies | Content decision | Established Agara as flagship simulation with two supporting documents. | Avoid over-investing in multiple simulations at preliminary stage. | Christopher Jones |  | Implemented | Maintain Agara terminology consistently.
CHG-003 | 2026-08-03 | 0.1.0 | Workbook architecture | Structural decision | Grouped planned Excel artefacts into three workbooks: umbrella, HHAS and CHUD. | Reduce fragmentation and version-control burden. | Christopher Jones |  | Implemented | Carry structure and ID conventions into detailed workbooks.